## Common
SW Validation List
Category | Sub-Category | No. | 관련 API or Test Item or GUI Path | OS | OCP | Description | 시작일 | 목표일정 | 완료일 | 결과 | 진행상황
PC Setup | HOST PC 변경 | 1 | Memory Check | O |  | DRAM 32GB 적용 여부 확인 | 2020-10-12 | 2020-11-03 | 2020-11-13 | PASS | 3대 중 3대 완료 추가 1대 진행중
|  | 2 | Network 환경 | O |  | Ehternet Port 에 대한 Option 설정 확인 |  |  |  |  | 3대 중 3대 완료 추가 1대 진행중
|  | 3 | Samba 환경 | O |  | Samba 연동 확인 |  |  |  |  | 3대 중 3대 완료 추가 1대 진행중
|  | 4 | Complier 환경 | O |  | GCC Compiler 환경 및 Makefile 점검 |  |  |  |  | 3대 중 3대 완료 추가 1대 진행중
|  | 5 | NFS 환경 | O |  | NFS 연동 Option 설정 확인 |  |  |  |  | 3대 중 3대 완료 추가 1대 진행중
|  | 6 | QT 환경 | O |  | QT LIB 버전 및 X11 Option 설정 확인 |  |  |  |  | 3대 중 3대 완료 추가 1대 진행중
GUI | Main Frame | 7 | Device Entry Setup | O |  | PCIE, UFS, ASI Device Entry 수정 필요
|  | 8 | DUT Map | O |  | 53k에 적용 되도록 DUT 수정 필요
|  | 9 | Lot Setup | O |  | Lot Setup 동작 확인
|  | 10 | Test | O | O | Test 진입 확인
|  | 11 | Stop | O | O | Test 중단 확인
|  | 12 | Lot Finish | O |  | Lot Finish 동작 확인(초기화 데이터)
|  | 13 | User Mode | O |  | 각 User Level 에 대한 정의 확인.
|  | 14 | Error Status | O |  | 각 Error Code 별 동작 확인
|  | 15 | Main Status | O | O | 장비 기본 상태 정보 표시 확인
|  | 16 | Dut Result Log | O | O | 변경된 Log 방식으로 Dut LOG가 정상적으로 저장되는지 확인 -> 기존 NFS로 LOG Data 저장 하는 방식에서 TCP로 packet을 전송하여 Host에서 log 저장
|  | 17 | GPIB Log | O |  | GPIB Communication Log 확인 (미정)
|  | 18 | Server Log | O |  | 상위 서버(SECS/GEM) Event Log 처리 확인 (미정)
| Utility | 19 | FW Downloader | O | O | PG image download가 정상적으로 동작 하는지 확인
|  | 20 | PCAL | O | O | 변경된 규격 검토 필요
|  | 21 | DIAG | O | O | 변경된 규격 검토 필요
|  | 22 | SYSCONDITION | O
|  | 23 | Analysis Tool | O | O
|  | 24 | Lotsetup | O |  | PG Mapping 검토 필요
Compiler | Socket | 25 | Compiler | O | O | Complile 정상 동작 확인 |  |  |  |  | Compile 결과 유효성 체크 진행 중
|  | 26 | ul_loadsocket() |  |  | 변경된 Socket File Loading 확인
| Pattern | 27 | Compiler | [7 empty] | FPGA 팀으로 부터 Map 문서 수령 및 Review 진행 완료
|  | 28 | ul_loadpat() |  |  | Pattern Loading 확인
BCB, DPB | Basic Interface | 29 | ul_syswrite() | O |  | H/W Team 검증용 BCB Write Function 동작 확인
|  | 30 | ul_sysread() | O |  | H/W Team 검증용 BCB Read Function 동작 확인
|  | 31 | ul_getctrlver() | O |  | CTRL 버전 체크 : HW에서 설정한 값과 동일하게 Read하는지 확인
|  | 32 | ul_getsubctrlver() | O |  | SUB CTRL 버전 체크 : HW에서 설정한 값과 동일하게 Read하는지 확인
|  | 33 | ul_getcpldver() |  |  | CPLD 버전 체크 : HW에서 설정한 값과 동일하게 Read하는지 확인
|  | 34 | ul_setbcbmask() | O |  | BCB Mask 체크 : HW Mask가 설정 되는지 확인 필요
|  | 35 | ul_getbcbid() | O |  | BCB ID 체크 : PGB ID가 정상적으로 읽히는지 확인
|  | 36 | ul_resetsubctrl() | O |  | Reset 체크 : sub ctrl의 Reset 확인
|  | 37 | ul_resetcpld() | O |  | Reset 체크 : cpld의 Reset 확인
| Fixed Power | 38 | ul_settbpower() | O |  | Fixed Power On/Off Seq 체크 : Fixed Power |  |  |  |  | Byte별 제어 에서 Bit별 제어로 변경됨
|  | 39 | ul_getadc() | O | O | ADC Data Read 동작 확인
| Flash | 40 | ul_loadctrlfiletoflash() |  |  | main ctrl, sub ctrl image downloader
|  | 41 | ul_checkctrlflashtofile() |  |  | main ctrl, sub ctrl image downloader
|  | 42 | ul_setctrlflasherase() | O |  | main ctrl, sub ctrl image downloader
|  | 43 | ul_checkctrlflasherase() | O |  | main ctrl, sub ctrl image downloader
|  | 44 | ul_setctrlflashwrite() | O |  | main ctrl, sub ctrl image downloader
|  | 45 | ul_checkctrlflashtofile() | O |  | main ctrl, sub ctrl image downloader
| PLL | 46 | ul_setdelayspan() |  |  | Pll Delay 설정 체크 : Pll Delay가 설정되는지 확인 |  |  |  |  | pll0 : 5.0 ns pll1 : 6.4 ns pll2 : 6.4 ns
|  | 47 | ul_setpll() | O |  | Pll 설정 체크 : Pll에 설정값이 정상적으로 적용 되는지 확인 |  |  |  |  | 4개 Pll에서 3개의 Pll로 변경됨
| PPS | 48 | ul_setdacinitpg | O | O | DAC Init & Clear |  |  |  |  | Code 만 준비 됨.
|  | 49 | ul_setadcreset | O | O | ADC Reset
|  | 50 | ul_setadcinitpg | O | O | ADC Init & Clear
|  | 51 | ul_set_dac() | O | O | PPS Power 설정 확인 |  |  |  |  | Code 만 준비 됨.
|  | 52 | ul_getadc() | O | O | ADC Data Read 동작 확인 |  |  |  |  | Code 만 준비 됨.
|  | 53 | ul_get_pps_adc() | O | O | Measure Mode, Signal Name 에 의한 PPS 측정값 확인 |  |  |  |  | Code 만 준비 됨.
|  | 54 | ul_set_pps_enable() |  | O | PPS Relay 제어용 함수 |  |  |  |  | Code 만 준비 됨.
|  | 55 | Pin Sharing |  | O
| PMU | 56 | ul_resetpmu() |  | O | Reset 체크 : pmu의 Reset 확인 |  |  |  |  | Reset seq 진행후 정상 동작 확인으로 확인 완료
|  | 57 | ul_init_pmu() |  | O | pmu chip의 초기화 진행 확인 |  |  |  |  | init seq 진행후 Voltage Force 정상 동작 확인으로 확인 완료
|  | 58 | ul_SetPmuVoltage() |  | O | PMU Voltage Setting 확인 |  |  |  |  | 해당 함수로 Voltage 출력후 ADC로 Measure하여 정상동작 확인
|  | 59 | ul_PmuMeasVoltage() |  | O | PMU Voltage Setting 확인 및 Measure 확인 |  |  |  |  | 해당 함수로 Voltage 출력후 ADC로 Measure하여 정상동작 확인
|  | 60 | ul_SetPmuCalRange() |  | O | Cal Range 저항 연결 확인 |  |  |  |  | Cal 저항 Path 연결을 DVM으로 확인 완료
|  | 61 | ul_SetPmuClampSet() |  | O | Pmu Clamp 동작 확인
|  | 62 | ul_SetPmuCurrent() |  | O | PMU Current Setting 확인
|  | 63 | ul_getadc() |  | O | ADC Data Read 동작 확인 |  |  |  |  | VSVM Path Setting 진행중
|  | 64 | ul_setrelay() |  | O | PMU Power 설정 확인
| HVDD | 65 |  |  | O
66
| DC-TEST | 67 |  |  | O
| Manual | 68
69
70
| DC-TEST | 71 |  |  | O
| Auto | 72
73
74
PCAL | Fixed Power | 75 | Fixed Power Check | O |  | 모든 Fixed Power 정상 유무 확인
| PPS | 76 | ul_setpcaldata() | O |  | Gain Register, offset Register 유무 확인 필요
|  | 77 | PPS Linearity | O |  | Full Range Linearity Check
|  | 78 | Cal Data | O |  | Cal 전, 후 Data 비교 평가
|  | 79 | Cal Data File Save / Load | O |  | Saved File and Load File Data Check
|  | 80 | CAL GUI | O |  | PPS Channel Port Check
| PMU | 81 | VSVM |  | O | VSVM CAL 정상 유무 확인 (정상 규격?, 5%, 10%???)
|  | 82 | ISIM |  | O | ISIM CAL 정상 유무 확인 (정상 규격?, 5%, 10%???)
|  | 83 | VCLAMP |  | O | VCLAMP 정상 유무 확인 (정상 규격?, 5%, 10%???)
|  | 84 | ICLAMP |  | O | ICLAMP 정상 유무 확인 (정상 규격?, 5%, 10%???)
|  | 85 | Cal Data File Save / Load |  | O | Saved File and Load File Data Check
| HVDD | 86 |  |  | O
87
| ADC | 88 |  |  | O | PPS, PMU, Fixed Power adc Cal 필요 여부 확인
DIAG | Version | 89 | Version Read & Display |  |  | Version 확인
| Fixed Power | 90 | Fixed Power Check | O | O | 모든 Fixed Power 정상 유무 확인
| Relay | 91 | Relay Check |  | O
| PPS | 92 | VSVM |  | O | Cal Load 이용하여 이상여부 확인
|  | 93 | VSIM |  | O | Cal Load 이용하여 이상여부 확인
|  | 94 | Voltage Clamp |  | O | Clamp 동작 확인 - Shutdown 검증 (with H/W Team) - Alarm 유무
|  | 95 | Current Clamp |  | O | Clamp 동작 확인 - Shutdown 검증 (with H/W Team) - Alarm 유무
| PMU | 96 | VSVM Check |  | O | Min Max Full Range 검사
|  | 97 | ISIM Check |  | O | Min Max Full Range 검사
|  | 98 | VCLAMP Check |  | O | Min Max Full Range 검사
|  | 99 | ICLAMP Check |  |  | Min Max Full Range 검사
| HVDD | 100 |  |  | O
101
| Temperature | 102 | Temperature Check |  | O | 온도 측정 가능한 Device 값 출력
GPIO |  | 103 |  |  |  | DUT당 21 Ea를 제어
104
Handler | GPIB | 105 | GPIB Access | O |  | Prober 업체 및 장비 선정 후 가능
|  | 106 | GPIB 통신 Scenario 확인 | O |  | Prober 업체 및 장비 선정 후 가능
107
108
109
Debug Uart | PG Uart | 110 | OCP UART to Ethernet Processor |  | O
|  | 111 | Host UART Log Processer |  | O
DOC | Manual 준비 | 112 | User API Reference
113

## Device-Type
SW 확인 List
Category | Sub-Category 1. | Sub-Category 2. | No. | 관련 API or Test Item or GUI Path | Description | 시작일 | 목표일정 | 완료일 | 결과 | 진행상황
Device Type(ASI) | PCI Core API | CFG common API | 1 | ul_cfg_read() | Run cfg read via PCI core interface.
|  |  | 2 | ul_cfg_read_rootcomplex() | Run cfg read to root complex via PCI core interface.
|  |  | 3 | ul_cfg_write() | Run cfg write via PCI core interface.
|  |  | 4 | ul_cfg_write_rootcomplex() | Run cfg write to root complex via PCI core interface.
|  |  | 5 | ul_pcie_capability_rootcomplex() | Get PCI capability offset on root complex.
|  |  | 6 | ul_pcie_configuration_rootcomplex() | Config PCI header of root complex via cfg.
|  |  | 7 | ul_pcie_getcapability() | Get capability value via CFG API.
|  |  | 8 | ul_pcie_setcapability() | Set capability value via CFG API.
|  | CFG device API | 9 | ul_cfg_read_device() | Run cfg read to device via PCI core interface.
|  |  | 10 | ul_cfg_write_device() | Run cfg write to device via PCI core interface.
|  |  | 11 | ul_pcie_compliance_test() | Enter compliance mode.
|  |  | 12 | ul_pcie_configuration_device() | Config PCI header of Device via cfg.
|  |  | 13 | ul_pcie_getcapability_device() | Get device's capability value via CFG API.
|  |  | 14 | ul_pcie_hwreset() | Configure device's PCIe header.
|  |  | 15 | ul_pcie_setcapability_device() | Set device's capability value via CFG API.
|  | PCIE common API | 16 | ul_get_rx_performance() | Get Rx performance.
|  |  | 17 | ul_get_tx_performance() | Get Tx performance.
|  |  | 18 | ul_memory_read() | Run memory read via PCI core interface.
|  |  | 19 | ul_memory_write() | Run memory write via PCI core interface.
|  |  | 20 | ul_pcie_link_check() | Wait until link is established.
|  |  | 21 | ul_pcie_link_reset() | Reset #PRSET Pin of Root Complex & Device.
|  |  | 22 | ul_tlp_moniter_printf_info() | Display TLPs stored in BRAM.
|  |  | 23 | ul_tlp_type_str() | Get TLP type string.
| HW Core API | peripheral common API | 24 | ul_set_device_voltage() | Set voltage value of device
|  |  | 25 | ul_get_device_voltage() | Read voltage value of device
|  |  | 26 | ul_get_device_current() | Read current value of device
|  |  | 27 | ul_set_gpio() | Set status of GPIO pin (High or Low)
|  |  | 28 | ul_get_gpio() | Get status of GPIO pin
| ASI Core API | ASI common API | 29 | ul_maple_bar0_mrd() | Run BAR0 memory read via PCI core interface.
|  |  | 30 | ul_maple_bar0_mwr() | Run BAR0 memory write via PCI core interface.
|  |  | 31 | ul_maple_bar2_mrd() | Run BAR2 memory read via PCI core interface.
|  |  | 32 | ul_maple_bar2_mwr() | Run BAR2 memory write via PCI core interface.
|  |  | 33 | ul_maple_select_bootmoder() | Select boot mode
|  | Data Operational Commands | 34 | ul_maple_read() | The Read command is used to read a segment of the multi-plane page Using Command : Read Command, Completion
|  |  | 35 | ul_maple_read_Verify() | The Read-Verify command performs a verification of data correctness of a block by reading and decoding a certain code word in the block, without transferring the data across PCI-E link back to the host. Using Command : Read-Verify Command, Completion
|  |  | 36 | ul_maple_write() | The Program command writes the data of a multi-plane operation to the NAND buffer. Using Command : Program Command, Completion
|  |  | 37 | ul_maple_write_exe() | The Program Execute command executes the program data to the NAND array to the physical address described by the previous Program command. Using Command : Program Execute Command, Completion
|  |  | 38 | ul_maple_erase() | The Block Erase command erases the blocks described in the PLANE_{0,1,2,3}_BLOCK field. Other physical address fields of the commands are not used and shall be set to 0. Using Command : Block Erase Command, Completion
|  | Data Debug Commands | 39 | ul_maple_read_without_sense() | The Read w/o Sense command is a command to read from the buffer of the NAND without sending a sense command to the NAND Using Command : Read w/o Sense command, completions(The command fields, completions, and system behavior are the same as Read command.)
|  |  | 40 | ul_maple_write_to_page_buffer() | The Program to Page buffer writes the data to the NAND page buffer without sending execute command to the NAND. Using Command : Program to Page buffer command, completions(The command fields, completions, and system behavior are the same as Program Raw command.)
|  |  | 41 | ul_maple_read_and_count_err() | The Read and Count Errors command is a Read Command that returns a counter of the fixed bits instead of the first 4 data bytes of each sector. Using Command : Read and Count Errors command, Completion(Command and completion formats are the same as Read command.)
|  |  | 42 | ul_maple_get_device_param() | The Get Device Parameters command returns Device Parameters Structure Using Command : Get Device Parameters command, Completion
|  |  | 43 | ul_maple_get_temp() | The Get Temperature command triggers a temperature measurement at spot close as possible to the hottest spot of the package. Using Command : Get Temperature Command, Completion
|  |  | 44 | ul_maple_get_health_mon_data() | The Read Health Monitor Data command returns the health monitor of a single plane page using up to 4 vendor-defined grades on the worst case ECC Chunk of the page. Using Command : Read Health Monitor Data command, Completion
|  |  | 45 | ul_maple_get_bad_block_bitmap() | The Get Bad Block Bitmap command returns the array of the bad blocks as burned in the factory settings for each die. Using Command : Get Bad Block Bitmap command, Completion
|  |  | 46 | ul_maple_set_power_state() | The Set System Power State command sets the power states. Using Command : Set System Power State command, Completion
|  |  | 47 | ul_maple_set_test_mode() | The Enable Test Modes command enables various tests mechanisms as shown below. Using Command : Enable Test Modes command, Completion
|  |  | 48 | ul_maple_get_device_context() | The Get Device Context command reads from the device the data that shall be retained during the device power cycle. Using Command : Get Device Context command, Completion
|  |  | 49 | ul_maple_set_device_context() | The Set Device Context command updates the device with the data that was retained during the device power cycle on the Host memory. Using Command : Set Device Context command, Completion
| Common API | Data Access | 50 | ul_maple_get_cm_to_file() | Save a saved Completion Message to file.
|  |  | 51 | ul_maple_write_userdata() | Store User Data in the buffer(Dram) from file.
|  |  | 52 | ul_maple_get_data_idx_region() | Read each IDX address data to file.
|  | Mode Select | 53 | ul_maple_set_idx_by_user() | Determines whether index is controlled by the user or by F/W. 0- unitest F/W, 1 - User
|  |  | 54 | ul_maple_set_cm_save_mode() | Determine whether to store SENSES or MEASURED_TIME in Completion Message 0-SENSES, 1-MEASURED_TIME, 2-NONE
|  |  | 55 | ul_maple_set_datapattern() | Determines the type of Data Pattern
|  |  | 56 | ul_maple_set_failmem_save_mode() | If an error occurs, decide whether to save it only or always. 0 : Save all, 1 : Save on error
|  |  | 57 | ul_maple_set_read_cmp_en() | Decide whether to do compare at read time. 0 : Normal, 1 : Compare Enable
|  |  | 58 | ul_maple_set_cm_save_en() | Determine whether to store Completion Message. 0 : Save Disable, 1 : Save Enable
|  |  | 59 | ul_maple_set_max_num_pe() | Max program number of program_execute group.( Internal Calculation Formula = 2^(cmd_num_set+1) ) enum CMD_NUM_SET{CMD_2EA=0, CMD_4EA, CMD_8EA, CMD_16EA, … };
|  |  | 60 | ul_maple_initalize_logic() | Determine the init mode Operation. enum INIT_MODE{NOMAL_OP=0, READ_OP, WRITE_OP};
Device Type(UFS) | HW Core API | peripheral common API | 1 | ul_set_pps_voltage() | Set voltage value of device
|  |  | 2 | ul_get_pps_voltagevcc() | Read VCC voltage value of device
|  |  | 3 | ul_get_pps_voltagevccq2() | Read VCCQ2 voltage value of device
|  |  | 4 | ul_get_pps_currentvcc() | Read VCC current value of device
|  |  | 5 | ul_get_pps_currentvccq2() | Read VCCQ2 current value of device
|  |  | 6 | ul_set_vth_sel() | Set Term voltage of PWM
|  |  | 7 | ul_cpld_device_reset() | Reset to device
|  |  | 8 | ul_cpld_tx_pwm_relay() | Set amplitude of PWM
|  |  | 9 | ul_cpld_discharge_relay() | Set discharge relay of PPS
| UFS Core API | Common API | 10 | ul_ufs_initialize_host() | Initialize host
|  |  | 11 | ul_ufs_send_UICCMD() | Send UIC command
|  |  | 12 | ul_ufs_get_UICCMD_rspcode() | Get UIC command response code ( UIC Command argument 2 )
|  |  | 13 | ul_ufs_get_UICCMD_MIB() | Get UIC command MIB value ( UIC Command argument 3 )
|  |  | 14 | ul_ufs_set_powermode() | Change power mode
|  |  | 15 | ul_ufs_set_hibernate_enter() | Set Hibernate Enter
|  |  | 16 | ul_ufs_set_hibernate_exit() | Set Hibernate Exit
|  | UPIU API | 17 | ul_ufs_set_nop_upiu() | Setting NOP UPIU & Request list
|  |  | 18 | ul_ufs_set_query_upiu() | Setting Query Request UPIU & Request list
|  |  | 19 | ul_ufs_set_taskmngt_upiu() | Setting Task Management Request UPIU & Task Management Request list
|  |  | 20 | ul_ufs_issue_reqlist() | Make Setting UTP Transfer Request list door bell
|  |  | 21 | ul_ufs_issue_taskmngtlist() | Make Setting UTP Task Management Request list door bell
|  |  | 22 | ul_ufs_check_reqlist() | Check Request List
|  |  | 23 | ul_ufs_check_taskmngtlist | Check Task Management Request List
|  | DataEngine API | 24 | ul_ufs_set_dataengine() | Setting to data engine
|  |  | 25 | ul_ufs_run_dataengine() | Run data engine
|  |  | 26 | ul_ufs_reset_dataengine() | Reset data engine
|  |  | 27 | ul_ufs_display_failmemory() | Display fail memory
|  | SCSI build API | 28 | ul_ufs_set_scsi_readcapacity10() | Make Read Capacity (10) Command and Command UPIU and UTP Transfer Request List
|  |  | 29 | ul_ufs_set_scsi_readcapacity16() | Make Read Capacity (16) Command and Command UPIU and UTP Transfer Request List
|  |  | 30 | ul_ufs_set_scsi_inquiry() | Make Inquiry Command and Command UPIU and UTP Transfer Request List
|  |  | 31 | ul_ufs_set_scsi_modeselect10() | Make Mode Select (10) Command and Command UPIU and UTP Transfer Request List
|  |  | 32 | ul_ufs_set_scsi_modesense10() | Make Mode Sense (10) Command and Command UPIU and UTP Transfer Request List
|  |  | 33 | ul_ufs_set_scsi_startstopunit() | Make Start Stop Unit Command and Command UPIU and UTP Transfer Request List
|  |  | 34 | ul_ufs_set_scsi_testunitready() | Make Test Unit Ready Command and Command UPIU and UTP Transfer Request List
|  |  | 35 | ul_ufs_set_scsi_reportlun() | Make Report LUN Command and Command UPIU and UTP Transfer Request List
|  |  | 36 | ul_ufs_set_scsi_verify10() | Make Verify (10) Command and Command UPIU and UTP Transfer Request List
|  |  | 37 | ul_ufs_set_scsi_requestsense() | Make Request Sense Command and Command UPIU and UTP Transfer Request List
|  |  | 38 | ul_ufs_set_scsi_formatunit() | Make Format Unit Command and Command UPIU and UTP Transfer Request List
|  |  | 39 | ul_ufs_set_scsi_prefetch10() | Make Prefetch (10) Command and Command UPIU and UTP Transfer Request List
|  |  | 40 | ul_ufs_set_scsi_prefetch16() | Make Prefetch (16) Command and Command UPIU and UTP Transfer Request List
|  |  | 41 | ul_ufs_set_scsi_securityprotocolin() | Make Security Protocol In Command and Command UPIU and UTP Transfer Request List
|  |  | 42 | ul_ufs_set_scsi_securityprotocolout() | Make Security Protocol Out Command and Command UPIU and UTP Transfer Request List
|  |  | 43 | ul_ufs_set_scsi_senddiagnostic() | Make Send Diagnostic Command and Command UPIU and UTP Transfer Request List
|  |  | 44 | ul_ufs_set_scsi_synchronizecache10() | Make Synchronize Cache (10) Command and Command UPIU and UTP Transfer Request List
|  |  | 45 | ul_ufs_set_scsi_synchronizecache16() | Make Synchronize Cache (16) Command and Command UPIU and UTP Transfer Request List
|  |  | 46 | ul_ufs_set_scsi_unmap() | Make Unmap Command and Command UPIU and UTP Transfer Request List
|  |  | 47 | ul_ufs_set_scsi_readbuffer() | Make Read Buffer Command and Command UPIU and UTP Transfer Request List
|  |  | 48 | ul_ufs_set_scsi_writebuffer() | Make Write Buffer Command and Command UPIU and UTP Transfer Request List
|  |  | 49 | ul_ufs_set_scsi_write6() | Make Write (6) Command and Command UPIU and UTP Transfer Request List
|  |  | 50 | ul_ufs_set_scsi_write10() | Make Write (10) Command and Command UPIU and UTP Transfer Request List
|  |  | 51 | ul_ufs_set_scsi_write16() | Make Write (16) Command and Command UPIU and UTP Transfer Request List
|  |  | 52 | ul_ufs_set_scsi_read6() | Make Read (6) Command and Command UPIU and UTP Transfer Request List
|  |  | 53 | ul_ufs_set_scsi_read10() | Make Read (6) Command and Command UPIU and UTP Transfer Request List
|  |  | 54 | ul_ufs_set_scsi_read16() | Make Read (6) Command and Command UPIU and UTP Transfer Request List
|  |  | 55 | ul_ufs_set_scsi_cmd() | Make Vender Command and Command UPIU and UTP Transfer Request List
| User Function | Common Function | 56 | user_shutdown() | Set off device voltage
|  |  | 57 | user_check_lane() | Check lane status after linkstartup
|  |  | 58 | user_check_powermode() | Check power mode status after set powermode change
|  |  | 59 | user_initial_device() | Initialize device
|  | Device Info. Function | 60 | user_readcapacity() | Get device's capability.
|  |  | 61 | user_devicedesc() | Get device descriptor information
|  |  | 62 | user_geometrydesc() | Get geometry descriptor information
|  |  | 63 | user_unitdesc() | Get unit descriptor information
|  |  | 64 | user_rpmb_unitdesc() | Get RPMB unit descriptor information
|  |  | 65 | user_powerdesc() | Get power descriptor information
|  |  | 66 | user_interconnectdesc() | Get interconnector descriptor information
|  |  | 67 | user_devicehealthdesc() | Get device health descriptor information
|  |  | 68 | user_manufacnamedesc() | Get string descriptor information ( manufacture name )
|  |  | 69 | user_productnamedesc() | Get string descriptor information ( product name )
|  |  | 70 | user_oemiddesc() | Get string descriptor information ( OEM ID )
|  |  | 71 | user_serialnumdesc() | Get string descriptor information ( Serial number )
|  |  | 72 | user_productrevleveldesc() | Get string descriptor information ( Product revision level )
|  |  | 73 | user_inpuiry_response() | Get inquery information
|  |  | 74 | user_request_sense() | Get request sense information
|  |  | 75 | user_modepage_control() | Get mode page information
|  |  | 76 | user_report_luns() | Get report LUN information
|  | Protocol Test Function | 77 | user_dataengine() | Set data engine and run data engine about write / read
|  |  | 78 | user_rpmb_program_key() | Set RPMB program key
|  |  | 79 | user_rpmb_auth_data() | Set RPMB authenticated data write/read
|  |  | 80 | user_rpmb_secure_blk() | Set RPMB secure block write/read
|  |  | 81 | user_unmap() | Set unmap
|  |  | 82 | user_selectpage() | Set select page
Device Type(NVME) | PCI Core API | CFG common API | 1 | ul_cfg_read() | Run cfg read via PCI core interface.
|  |  | 2 | ul_cfg_read_rootcomplex() | Run cfg read to root complex via PCI core interface.
|  |  | 3 | ul_cfg_write() | Run cfg write via PCI core interface.
|  |  | 4 | ul_cfg_write_rootcomplex() | Run cfg write to root complex via PCI core interface.
|  |  | 5 | ul_pcie_capability_rootcomplex() | Get PCI capability offset on root complex.
|  |  | 6 | ul_pcie_configuration_rootcomplex() | Config PCI header of root complex via cfg.
|  |  | 7 | ul_pcie_getcapability() | Get capability value via CFG API.
|  |  | 8 | ul_pcie_setcapability() | Set capability value via CFG API.
|  | CFG device API | 9 | ul_cfg_read_device() | Run cfg read to device via PCI core interface.
|  |  | 10 | ul_cfg_write_device() | Run cfg write to device via PCI core interface.
|  |  | 11 | ul_pcie_compliance_test() | Enter compliance mode.
|  |  | 12 | ul_pcie_configuration_device() | Config PCI header of Device via cfg.
|  |  | 13 | ul_pcie_getcapability_device() | Get device's capability value via CFG API.
|  |  | 14 | ul_pcie_hwreset() | Configure device's PCIe header.
|  |  | 15 | ul_pcie_setcapability_device() | Set device's capability value via CFG API.
|  | PCIE common API | 16 | ul_get_rx_performance() | Get Rx performance.
|  |  | 17 | ul_get_tx_performance() | Get Tx performance.
|  |  | 18 | ul_memory_read() | Run memory read via PCI core interface.
|  |  | 19 | ul_memory_write() | Run memory write via PCI core interface.
|  |  | 20 | ul_pcie_link_check() | Wait until link is established.
|  |  | 21 | ul_pcie_link_reset() | Reset #PRSET Pin of Root Complex & Device.
|  |  | 22 | ul_tlp_moniter_printf_info() | Display TLPs stored in BRAM.
|  |  | 23 | ul_tlp_type_str() | Get TLP type string.
| HW Core API | peripheral common API | 24 | ul_set_device_voltage() | Set voltage value of device
|  |  | 25 | ul_get_device_voltage() | Read voltage value of device
|  |  | 26 | ul_get_device_current() | Read current value of device
|  |  | 27 | ul_set_gpio() | Set status of GPIO pin (High or Low)
|  |  | 28 | ul_get_gpio() | Get status of GPIO pin
| NVMe Core API | NVMe common API | 29 | ul_nvme_controller_initialization | Enable controller and set ASQ/ACQ base address & MSI-X table
|  |  | 30 | ul_nvme_controller_shutdown | Disable controller and reset Dut via PCIe_CR register
|  |  | 31 | ul_nvme_create_cqsq | Create I/O completion Queue and Submission Queue
|  |  | 32 | ul_nvme_delete_cqsq | Delete I/O completion Queue and Submission Queue
|  |  | 33 | ul_nvme_issue_admincmd | Set ASQ tail doorbell on the assumption that command is inserted in ASQ, and process ACQ Rx
|  |  | 34 | ul_nvme_issue_nvmecommand | Issue NVMe command
|  | Data Operational Commands | 35 | ul_nvme_memory_read | Run NVMe memory read via PCI core interface
|  |  | 36 | ul_nvme_memory_write | Run NVMe memory write via PCI core interface
|  |  | 37 | ul_nvme_set_admincmd_prpbram | Insert a command in Admin Submission Queue that references PRP in BRAM
|  |  | 38 | ul_nvme_get_admincmd_prpbram | Get the address of BRAM that stores the read data
| Common API | Data Debug Commands | 39 | ul_nvme_clear_failmemory | Clear fail memory
|  |  | 40 | ul_nvme_clear_nvmecommand | Clear NVMe command
|  |  | 41 | ul_nvme_get_nvmecommand_iocq | Check completion set
|  |  | 42 | ul_nvme_get_admincmd_completionqueue | Get a completion from ACQ
|  |  | 43 | ul_nvme_get_temperature | Issue a get log command and return temperature
|  |  | 44 | ul_nvme_get_failmemory_head | Get first fail memory entry
|  |  | 45 | ul_nvme_display_failmemory | Display fail memory
|  |  | 46 | ul_nvme_copy_prpbram | Copy data to target buffer from BRAM